## PracticeLab_ProjectTasks_J2EE
Classroom Session | Mentor Involvement | Sl No | Task | Sub Task | Mode | Generated Output | Effort (hrs per person)
91
|  | 1 | Environment setup |  |  |  |  | 7
Software Engineering |  | 1.01 |  | Install version control client tool | Guided by Trainer | Tool installed and configured | 0.5
|  | 1.02 |  | Get the artifacts of the project from the version control server | Self | Documents in the local desktop | 0.5
|  | 1.03 |  | Understand the version control tool features | Guided by Trainer | Tried all the features available in the tool | 2
|  | 1.04 |  | Understand the usage of Defect tracking tool | Guided by Trainer | Tried all the features available in the tool | 2
OOPs |  | 1.05 |  | Install the compiler - JDK | Guided by Trainer | Tool installed and configured | 0.25
|  | 1.06 |  | Install the IDE - Eclipse & subclipse | Guided by Trainer | Tool installed and configured | 0.25
|  | 1.1 |  | Install Database - MySQL | Guided by Trainer | Tool installed and configured | 0.25
XML |  | 1.07 |  | Install the XML Parser & Xpontus | Guided by Trainer | Tool installed and configured | 0.25
J2EE |  | 1.08 |  | Install the Web/Application server | Guided by Trainer | Tool installed and configured | 0.25
|  | 1.09 |  | Install Struts, hibernate | Guided by Trainer | Tool installed and configured | 0.25
|  | 1.12 |  | Setup ANT tool | Guided by Trainer | Tool installed and configured | 0.25
|  | 1.13 |  | Install and configure JUDE-Astah tool | Guided by Trainer | Tool installed and configured | 0.25
|  | 2 | Project Briefing |  |  |  |  | 5
| Mentor | 2.01 |  | Explain the Project Lifecycle and map to OMS links | SME | Engineers will understand how to use the templates and guidelines | 0.5
| Mentor | 2.02 |  | Explain the OMS templates used in this project | SME | Engineers will understand the templates in detail. | 2
| Mentor | 2.03 |  | Expain the schedule, milestones, process to be followed in the project. | SME | Engineers will how the project is executed and the milestone dates and process to be followed. | 1
| Mentor | 2.04 |  | Explain and handover the practice lab manual | SME | Engineers understand the Practice Lab manual content | 0.5
| Mentor | 2.05 |  | Explain the SRS and Requirements Analysis Sheet | SME | Explain high level functionalities and about each section headings. | 0.5
|  | 2.06 |  | Understand the usage of issue log for clarifications | Guided by Trainer | Understand how to fill the document | 0.5
|  | 3 | Configure the application |  |  |  |  | 4
|  | 3.01 |  | Get the source code from the version control server | Guided by Trainer | Source code available in the desktop | 0.5
|  | 3.02 |  | Configure the application in the IDE. | Guided by Trainer | Configured application and able to compile | 1
|  | 3.03 |  | Deploy the application using the IDE. | Guided by Trainer | Able to deploy the application in App Server | 1
|  | 3.04 |  | Integrate the application server and database with the IDE | Guided by Trainer | DB scripts are run, Application is able to connect to DB | 1
|  | 3.05 |  | Debug the application using the IDE | Guided by Trainer | Able to set breakpoints and debug the application. | 0.5
|  | 4 | System Study |  |  |  |  | 6
|  | 4.02 |  | Understand Requirements Analysis sheet. | Self | Understand the requirements | 2
Webservices |  | 4.03 |  | Understand SRS document | Self | Understand the requirements | 2
Design Patterns |  | 4.04 |  | Raise the clarifications in Issue Log. | Self | Issue log checked in to the Ver Cntl server | 0.5
|  | 4.05 |  | Clarify the doubts raised in Issue Log. | SME | Checkin the Issue log. | 0.5
|  | 4.06 |  | Understand the clarifications | Self | Issue log checked in to the Ver Cntl server | 1
|  | 5 | Testing |  |  |  |  | 9.5
Struts |  | 5.01 |  | Understand the Test Plan and Strategy | Self | Understand how to execute the test cases | 1
|  | 5.02 |  | Understand the test cases | Self | Understand how the test cases are written for different scenarios. | 2
Hibernate |  | 5.03 |  | Execute the test cases | Self | Execute the test case and update the test report and log the defects. | 4
|  | 5.04 |  | Log the defects | Self | Log the defects in Defect tracking tool | 1
|  | 5.05 |  | Prepare and Checkin the test reports | Self | Checkin in the Test Reports | 1
|  | 5.06 |  | Review the defects logged | Peer review | Verify if all the defects have been captured and logged in the defect tracking tool. | 0.5
|  | 6 | Defect Fixing |  |  |  |  | 28
Project |  | 6.01 |  | Understand the defects and reproduce the defects | Self | Able to reproduce the defects | 2
|  | 6.02 |  | Understand HLD | Self | Understand the Architecture and layers of the application | 1
|  | 6.03 |  | Understand LLD | Self | Understand the classes and files associated with the application | 2
|  | 6.04 |  | Understand jUnit Test Cases | Self | Understand the unit test cases and how it should be executed for this project. | 0.5
|  | 6.05 |  | Understand RTM | Self | Understand the RTM | 0.5
|  | 6.06 |  | Analyze the defects | Self | Able to identify the location in which the defect has occurred along with the solution | 9
|  | 6.07 |  | Prepare Resolution document | Self | Prepared the document | 1
|  | 6.08 |  | Review of Resolution document | Peer review | Provide review comments | 0.25
|  | 6.09 |  | Incorporate review comments | Self | Updated document | 0.25
|  | 6.1 |  | Source code changes | Self | Modified source code | 9
|  | 6.11 |  | Review of source code | Peer review | Provide review comments | 0.5
|  | 6.12 |  | Incorporate review comments | Self | Updated source code | 0.5
|  | 6.13 |  | Peer Unit Testing | Self | Log the defects in Defect tracking tool | 0.25
|  | 6.14 |  | Defect Fixing | Self | Updated source code | 0.25
|  | 6.15 |  | Soure code Integration | Self | Merge and checkin the source code | 0.5
|  | 6.16 |  | Release Notes | Self | Prepared the document | 0.5
|  | 7 | Enhancements |  |  |  |  | 22.5
|  | 7.01 |  | Understand the enhancements requirements | Self | Understand the requirements | 0.5
|  | 7.02 |  | Update SRS | Self | Updated document | 0.5
|  | 7.03 |  | Review of SRS changes | Peer review | Provide review comments | 0.25
|  | 7.04 |  | Incorporate review comments | Self | Updated document | 0.25
|  | 7.05 |  | Update Functional Test cases | Self | Updated document | 1
|  | 7.06 |  | Review of Functional Test cases | Peer review | Provide review comments | 0.25
|  | 7.07 |  | Incorporate review comments | self | Updated document | 0.25
| Mentor | 7.08 |  | Update Design document | Self | Updated document | 0.5
| Mentor | 7.09 |  | Review of Design document | Peer review | Provide review comments | 0.25
| Mentor | 7.1 |  | Incorporate review comments | Self | Updated document | 0.25
|  | 7.11 |  | Prepare maintenance RTM | Self | Updated document | 0.5
|  | 7.12 |  | Review of RTM | Peer review | Provide review comments | 0.25
|  | 7.13 |  | Incorporate review comments | Self | Updated document | 0.25
| Mentor | 7.14 |  | Prepare Resolution document | Self | Prepared the document | 1
| Mentor | 7.15 |  | Review of Resolution document | Peer review | Provide review comments | 0.25
| Mentor | 7.16 |  | Incorporate review comments | Self | Updated document | 0.25
|  | 7.17 |  | Source code changes | Self | Updated source code | 9
| Mentor | 7.18 |  | Review of source code | Peer review | Provide review comments | 0.5
| Mentor | 7.19 |  | Incorporate review comments | Self | Updated source code | 0.5
| Mentor | 7.2 |  | Udpate Unit Test cases | Self | Updated source code | 3
|  | 7.21 |  | Review Unit Test cases | Peer review | Provide review comments | 0.5
|  | 7.22 |  | Incorporate review comments | Self | Updated source code | 0.5
|  | 7.23 |  | Peer Unit Testing | Self | Log the defects in Defect tracking tool | 1
|  | 7.24 |  | Defect Fixing | Self | Updated source code | 1
|  | 8 | Integration and Deployment |  |  |  |  | 9
|  | 8.01 |  | Source code integration | Self | Merge and checkin the source code | 2
|  | 8.02 |  | Deployment in the server | Self | Application deployed in the server | 0.5
|  | 8.03 |  | Remote debug using the IDE | Guided by Trainer | Able to set breakpoints and debug the application. | 2
|  | 8.04 |  | Release Notes | Self | Prepared the document | 0.5
|  | 8.05 |  | Peer Functional testing | Self | Log the defects in Defect tracking tool | 2
|  | 8.06 |  | Defect Fixing | Self | Updated source code | 1
|  | 8.07 |  | Final deployment | Self | Application deployed in the server | 0.5
|  | 8.08 |  | Verification of deployment | Peer review | Provide review comments | 0.5

## Calendar
| Blue--> | Practice Lab |  | Pink--> | Theory Session Technical |  | Grey--> | Foundation |  | Training Start Date --> | 2011-05-13
Day | 9:00am to 10:00am | 10:00am to 11:00am | Break | 11:15am to 12:15am | 12:15pm to 1:15pm | Break | 2:00pm to 3:00pm | 3:00pm to 4:00pm | Break | 4:15pm to 5:15pm | 5:15pm to 6:15pm | Break | 6:30pm to 7:00pm | Date | No of Holidays/additonal days
1 | Software Engineering | Software Engineering |  | Software Engineering | Software Engineering |  | Software Engineering | Software Engineering |  | Software Engineering | Software Engineering |  | Software Engineering | 2011-05-13
2 | NIL | Software Engineering |  | Software Engineering | Software Engineering |  | NIL | NIL |  | Software Engineering | Software Engineering |  | Software Engineering | 2011-05-16 | 1
| 1) Install version control client tool 2) Get the artifacts of the project from the version control server | [5 empty] | 1) Understand the version control tool features | 1) Understand the version control tool features
3 | NIL | NIL |  | Software Engineering | Software Engineering |  | Software Engineering | Software Engineering |  | Software Engineering | Software Engineering |  | Software Engineering | 2011-05-17
| 1) Understand the usage of Defect tracking tool | 1) Understand the usage of Defect tracking tool
4 | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | 2011-05-18
1) Install Database
5 | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | 2011-05-19
6 | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | 2011-05-20
7 | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | RDBMS |  | RDBMS | 2011-05-21
8 | Softskill | Softskill |  | Softskill | Softskill |  | Softskill | Softskill |  | Softskill | Softskill |  | Softskill | 2011-05-23
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
8 | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | Unix |  | Unix | 2011-05-23 | -1
9 | NIL | 45MINS Theory Session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-24
1) Install the compiler - JDK 2) Install the IDE - Eclipse
10 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-25
11 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-26
12 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-27
13 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-28
14 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-30
15 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-05-31
16 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-01
17 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-02
18 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-03
19 | 45 min Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-04
1) Install the XML Parser
20 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-06
21 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-07
22 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-08
23 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-09
24 | NIL | 45 min Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-10
| 1) Install the Web/Application server 2) Install Struts, hibernate 3) Install Putty & winscp 4) Setup ANT tool | 1) Install and configure JUDE-Astah tool
25 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-11
26 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-13
27 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-14
28 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-15
29 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-16
30 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-17
31 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-18
32 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-20
33 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-21
34 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-22
35 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | 2011-06-23
36 | Theory session | Theory session |  | Theory session | Theory session |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-06-24
[7 empty] | 1) Explain the Project Lifecycle and map to OMS links 2) Explain the OMS templates used in this project | 2) Explain the OMS templates used in this project |  | 2) Explain the OMS templates used in this project 3) Expain the schedule, milestones, process to be followed in the project. | 3) Expain the schedule, milestones, process to be followed in the project. 4) Explain and handover the practice lab manual |  | 5) Explain the SRS and Requirements Analysis Sheet
37 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | 30 min Theory session | NIL |  | NIL | 2011-06-25
[10 empty] | 1) Understand the usage of issue log for clarifications | 2) Get the source code from the version control server 3) Configure the application in the IDE. |  | 3) Configure the application in the IDE.
38 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | NIL | NIL |  | NIL | 2011-06-27
[10 empty] | 1) Deploy the application using the IDE. | 2) Integrate the application server and database with the IDE |  | 3) Debug the application using the IDE
39 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | 30 min Theory session | NIL |  | NIL | 2011-06-28
[10 empty] | 1) Understand Requirements Analysis sheet. | 1) Understand Requirements Analysis sheet. |  | 1) Understand Requirements Analysis sheet.
40 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | 30 min Theory session | NIL |  | NIL | 2011-06-29
[10 empty] | Understand SRS document | Understand SRS document |  | Understand SRS document
41 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | 30 min Theory session | NIL |  | NIL | 2011-06-30
[10 empty] | 1) Raise the clarifications in Issue Log. | 2) Clarify the doubts raised in Issue Log. 3) Understand the clarifications |  | 3) Understand the clarifications
42 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | NIL | NIL |  | NIL | 2011-07-01
[10 empty] | 1) Understand the Test Plan and Strategy | 1) Understand the test cases |  | 1) Understand the test cases
43 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | NIL | NIL |  | NIL | 2011-07-02
[10 empty] | 1) Understand the test cases Execute the test cases | Execute the test cases |  | Execute the test cases
44 | Theory session | Theory session |  | Theory session | Theory session |  | Theory session | Theory session |  | 30 min Theory session | NIL |  | NIL | 2011-07-04
[10 empty] | Execute the test cases | Execute the test cases |  | Execute the test cases
45 | Theory session | Theory session |  | Theory session (Junit) | Theory session (Junit) |  | Theory session (Junit) | Theory session (Junit) |  | NIL | NIL |  | NIL | 2011-07-05
[10 empty] | Log the defects | Prepare and Checkin the test reports |  | Review the defects logged
46 | EXIT TEST | EXIT TEST |  | EXIT TEST | EXIT TEST |  | Process Training | Process Training |  | Process Training | Process Training |  | Process Training | 2011-07-06
47 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-07
| Understand the defects and reproduce the defects | Understand the defects and reproduce the defects |  | Understand HLD | Understand LLD |  | Understand LLD | Understand JUnit Test Cases Understand RTM |  | Analyze the defects | Analyze the defects |  | Analyze the defects
48 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-08
| Analyze the defects | Analyze the defects |  | Analyze the defects | Analyze the defects |  | Analyze the defects | Analyze the defects |  | Analyze the defects Prepare Resolution document | Prepare Resolution document Review of Resolution document Incorporate review comments |  | Source code changes
49 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-09
| Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes
50 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-11
| Review of source code Incorporate review comments | Peer Unit Testing Defect Fixing Soure code Integration |  | Release Notes Understand the enhancements requirements | Prepare Resolution document |  | Review of Resolution document Incorporate review comments Update Design document | Review of Design document Incorporate review comments Update SRS |  | Review of SRS changes Incorporate review comments Update Functional Test cases | Update Functional Test cases Review of Functional Test cases Incorporate review comments |  | Prepare maintenance RTM
51 | NIL | NIL |  | NIL | NIL |  |  | NIL |  | NIL | NIL |  | NIL | 2011-07-12
| Review of RTM Incorporate review comments Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes | Source code changes |  | Source code changes
52 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-13
| Source code changes | Review of source code Incorporate review comments |  | Udpate Unit Test cases | Udpate Unit Test cases |  | Udpate Unit Test cases | Review Unit Test cases Incorporate review comments |  | Peer Unit Testing | Defect Fixing |  | Source code integration
53 | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | 2011-07-14
| Source code integration | Source code integration Deployment in the server |  | Remote debug using the IDE | Remote debug using the IDE |  | Release Notes Peer Functional testing | Peer Functional testing |  | Peer Functional testing Verification of deployment | Defect Fixing |  | Final deployment